## Product Backlog
Product Name: | ELSA Store | [6 empty] | Complete Fields in Green!!!
Team ID: | The Scrummers
| Team Member Name | [5 empty] | Initials | Student ID
Required | Brandon Faulkner | [5 empty] | BF | 1001988125
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 24 |  |  |  | Total | Total number of features (in column H)
1 | 19 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 12 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 7 | 5 |  |  | 3 | ...and so on
4 | 2 | 5
5 | 2 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
[5 empty] | Sprint to which Feature is Assigned |  |  | Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly | Validate the email address (lightly)
OPT | 2 | 1 |  | 3 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product | Validate that the cost is not negative
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
STORE | 5 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Provide a central collection of the above data | Create and manage information to run my store efficiently
WIN | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | Sales Staff | Add a GUI main window with menubar | Use it more easily | Recommend baselining Nim from Lecture 12
INSCU | 7 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Customers via a sequence of dialogs | Do everything within the GUI | Recommend JOptionDialog from Lecture 13
INSOP | 8 | 2 |  | 3 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Options via a sequence of dialogs | Do everything within the GUI
INSCO | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Computers via a sequence of dialogs | Do everything within the GUI
DISP | 10 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | List data (customers, options, and computers separately) in the main window display | Access the data directly in the window | You’ll need a View menu for this, and perhaps a JLabel in the main window center section
TOOLB | 11 | 2 |  | 8 | 2 | Finished in Sprint 2 | Sales Staff | Add a simple toolbar to the main window | Use the app with pushbutton convenience | Part of the Nim baseline. Create your own icons or find some online.
ABOUT | 12 | 3 |  | 2 | 2 | Finished in Sprint 2 | Director | (If needed) Provide a simple text-only About dialog | Avolid a lawsuit | (If needed) Rewrite the text from Nim's implementation to comply with toolbar icon license obligations
ABOSK | 13 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Provide About dialog with sketch as or around a bitmap logo for aesthetics and documenting licenses | Impress users | Recommend a subclass of JPanel from Lecture 15 with a simple diagram plus Jlabels in one or more JPanels with program information
SAVE | 14 | 3 |  | 13 | 3 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save (via method) and reload (via constructor) each object from a provided stream
NEW | 15 | 3 |  | 1 | 3 | Finished in Sprint 3 | Manager | Create a new, empty store | Start new franchises | This is as easy as “new Store” with a name
SAVAS | 16 | 3 |  | 5 | 3 | Finished in Sprint 3 | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use JfileChooser
LOAD | 17 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use JfileChooser
INSOR | 18 | 4 |  | 5 | 4 | Finished in Sprint 4 | Sales Staff | Insert new Orders via a sequence of dialogs | Do everything within the GUI
OCOST | 19 | 4 |  | 5 | 4 | Finished in Sprint 4 | Sales Staff | Calculate and display total cost of order | Know how much to charge the customer
DISP2 | 20 | 4 |  | 2 | 4 | Finished in Sprint 4 | Sales Staff | List ORDERS in the main window display | Access the order data | This is a minor change
DCUST | 21 | 4 |  | 13 | 4 | Finished in Sprint 4 | Sales Staff | Replace sequencial dialogs with custom dialogs | Enter data more quickly | More practice with custom dialogs (just Insert Customer & Option here) - INCLUDE icon used on button in the dialog
UNIQ | 22 | 5 |  | 8 |  |  | Manager | Avoid duplicate data entry | Keep the database clean | Use a HashSet for Store Lists with valid hashCode implementations for the 4 store data classes
SORT | 23 | 5 |  | 5 |  |  | Sales Staff | Sort customer names | Find customers more quickly | Use a TreeSet for the Customer list in Store
GSAVE | 24 | 5 |  | 13 |  |  | Director | Reduce lines of code | Save money on maintenance contracts | Use a generic save method for all Lists in the Store
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
SCROL |  |  | 10 | 5 |  | Finished in Sprint 4 | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR |  |  | 25 | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR |  |  | 15 | 8 |  |  | Manager | Add a status bar to the main window | Better track status of messages | A stack of messages that can be reviewed would be worth more!
DTAIL |  |  | 40 | 21 |  |  | Customer | Provide a detail view of a product type info in the main window, including a picture | Provide additional info about each product | The image can be a file. Store the filename in Option, and load from disk when required
SPEC |  |  | 25 | 13 |  |  | Customer | Store and display type-specific data | Ensure I purchase the correct product | Use inheritance with polymorphism

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2023-02-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-02-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 10 | 0
Day 2 Left | 10 | 0
Day 3 Left | 10 | 0
Day 4 Left | 10 | 0
Day 5 Left | 0 | 10
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | CUST |  | Write Customer Class | Completed Day 5
2 | CUST |  | Add Customer.java to GitHub | Completed Day 5
3 | OPT |  | Write Option Class | Completed Day 5
4 | OPT |  | Add Option.java to Github | Completed Day 5
5 | DESKT |  | Write Computer Class | Completed Day 5
6 | DESKT |  | Add Computer.java to Github | Completed Day 5
7 | ORDER |  | Write Order Class | Completed Day 5
8 | ORDER |  | Add Order.java to Github | Completed Day 5
9 | STORE |  | Use provided Store Class | Completed Day 5
10 | STORE |  | Add Store.java to Github | Completed Day 5
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2023-02-28 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 8 | 0
Day 2 Left | 8 | 0
Day 3 Left | 8 | 0
Day 4 Left | 8 | 0
Day 5 Left | 4 | 4
Day 6 Left | 0 | 4
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | Reimplement Nim Game Window into ELSA Store Window | Completed Day 5
2 | INSCU |  | Implemented a method to insert customers through a JOptionPane | Completed Day 5
3 | INSOP |  | Implemented a method to insert options through a JOptionPane | Completed Day 5
4 | INSCO |  | Implemented a method to insert computers through a JOptionPane | Completed Day 5
5 | DISP |  | Implemented a method to view customers,options and computers on the main display | Completed Day 6
6 | TOOLB |  | Reimplement toolbar from Nim Game into the 3 insert and 3 view buttons | Completed Day 6
7 | ABOUT |  | Reimplement about dialog from Nim Game | Completed Day 6
8 | WIN |  | Add new package directories store and gui into Github | Completed Day 6
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2023-03-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 10 | 0
Day 2 Left | 10 | 0
Day 3 Left | 10 | 0
Day 4 Left | 10 | 0
Day 5 Left | 0 | 10
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVE |  | Added save methods to each "store" class | Completed Day 5
2 | SAVE |  | Added onSaveClick method to MainWin | Completed Day 5
3 | SAVE |  | Added new "Save File" icon to toolbar | Completed Day 5
4 | NEW |  | Added onNewClick method to MainWin | Completed Day 5
5 | NEW |  | Added new "New Store" icon to toolbar | Completed Day 5
6 | SAVAS |  | Added onSaveAsClick method to MainWin | Completed Day 5
7 | SAVAS |  | Added new "Save File As" icon to toolbar | Completed Day 5
8 | LOAD |  | Added new constructors to each "store" class | Completed Day 5
9 | LOAD |  | Added onOpenClick method to MainWin | Completed Day 5
10 | LOAD |  | Added new "Open File" icon to toolbar | Completed Day 5
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2023-04-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 5 | 0
Day 3 Left | 5 | 0
Day 4 Left | 5 | 0
Day 5 Left | 0 | 5
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | INSOR |  | Finished the onInsertOrderClick method | Completed Day 5
2 | OCOST |  | Added total cost of order to the order display | Completed Day 5
3 | DISP2 |  | Set up onInsertOrderClick to display on main window using onViewClick | Completed Day 5
4 | DCUST |  | Made every dialog a single dialog instead of multiple | Completed Day 5
5 | SCROL |  | Made the main window display have a scroll feature for large amounts of data | Completed Day 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2023-04-18 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-25
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 3 | 0
Day 2 Left | 3 | 0
Day 3 Left | 3 | 0
Day 4 Left | 3 | 0
Day 5 Left | 3 | 0
Day 6 Left | 0 | 3
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | UNIQ |  | Added hashCode method to Customer, Option, Computer and Order and switched the ArrayLists in Store to HashSets | Completed Day 6
2 | SORT |  | Updated Customer to implement Comparable and changed it to a TreeSet in Store | Completed Day 6
3 | GSAVE |  | Created Saveable interface and implemented a generic save method in Store | Completed Day 6
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 6 | BONUS | Complete Fields in Green!!!
Start on | 2023-04-25 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-05-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
NOTE: This sprint is entirely OPTIONAL – no points will be lost if you ignore it
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84